Department of Science & Technology (DST)

Project Title:

Decentralized Blockchain-Based Framework for Secure Electronic Health Record Sharing

Abstract:

This research proposes a decentralized, blockchain-based system for secure and privacy-preserving electronic health record (EHR) sharing between multi-specialty hospitals. The framework will utilize blockchain technology and advanced cryptographic techniques to ensure patient confidentiality and data integrity, enabling hospitals to share EHRs in a secure, transparent, and tamper-proof manner.

Objectives:

Design and develop a decentralized blockchain-based system for secure EHR sharing
Implement advanced cryptographic techniques, such as homomorphic encryption and zero-knowledge proofs, to ensure patient data confidentiality
Develop access control and authentication mechanisms for hospitals and healthcare professionals
Ensure data standardization and interoperability for seamless EHR sharing
Optimize the system for scalability and performance in large-scale EHR sharing scenarios
Ensure regulatory compliance and patient consent management

Methodology:

The research will employ a combination of literature review, surveys, and interviews to identify requirements and challenges, followed by the design and development of a prototype blockchain-based EHR sharing system. Simulation-based testing and evaluation will be conducted to assess the system's performance and security, and a pilot deployment will be carried out in a real-world hospital setting.

Expected Results:

The proposed framework is expected to provide a secure, efficient, and patient-centric solution for EHR sharing between hospitals, with potential benefits including improved patient outcomes, reduced healthcare costs, enhanced patient privacy and confidentiality, and increased trust in the healthcare system.

Timeline:

The research is expected to be completed within 24 months, with the following milestones: months 1-6 (literature review and requirements gathering), months 7-12 (prototype development and testing), months 13-18 (pilot deployment and evaluation), and months 19-24 (finalization of results and reporting)

Budget:

Personnel: 3000000

Equipment: 500000

Software: 200000

Misc: 250000

Total: 3750000

Evaluation:

Innovation: 0

Feasibility: 0

Clarity: 0

Final Score: 87.5

Generated On:

2026-04-13 00:08